BSAAI CAPSTONE PROPOSAL

PROWL

Pancreatic Review and Outlining

Workflow for Lesions

An Autonomous Pancreatic Lesion Annotation and Radiologist Review System

Quinton Evans

Bachelor of Science in Applied Artificial Intelligence and Data Engineering

August 25, 2026

# 1. Motivation and Purpose

Medical imaging matters to me because the distance between what a scan contains and what a clinician can act on has affected my family directly. In 1998 my grandfather had a stroke. The initial angiogram did not reveal the clot, and the event was recorded as a transient ischemic attack. The clot was found months later, after the damage was permanent. He lived with dementia for the rest of his life and died last year. That experience is why the gap between an image and an actionable understanding is not an abstract problem to me.

There is also a long history of healthcare in my family. My step-grandfather spent his career as a radiologist, my mother began radiology school, and my grandfather worked in healthcare leadership at Intermountain Healthcare. Johns Hopkins research shaped many of the clinical practices he followed. My aunt is a diagnostic care coordinator who schedules biopsies, works with CT imaging, and helps patients understand what their imaging showed. When I described this project to her, she explained why pancreatic imaging is especially difficult in practice.

I chose pancreatic imaging because it is a meaningful technical challenge. The pancreas is soft tissue, varies substantially between patients, and sits in a crowded part of the abdomen. Small lesions can be difficult to distinguish even when someone is looking directly at the correct region. Software that locates the organ, proposes contours, and brings a reviewer to a suspicious area does not replace that reviewer’s judgment. It helps the human reach the right part of the image and keeps the human decision at the center of the workflow.

# 2. Project Overview and Intended User

This capstone will build an autonomous pancreatic-lesion annotation-assist system for radiologists and radiology clinicians reviewing abdominal CT. When a scan enters the system, the imaging pipeline will locate the pancreas, outline the organ and any suspected lesion, calculate useful measurements, and assign a score that helps order the review worklist. The reviewer will see the scan and proposed contours, then accept, edit, or reject them. That decision will be stored as part of the system’s correction and limitation history.

Why PROWL. PROWL stands for Pancreatic Review and Outlining Workflow for Lesions. The name follows the intended workflow: the system locates the pancreas, outlines suspected lesions, and returns its proposed contours to a radiologist for review, editing, or rejection.

The present limitation. A model developed during the preceding project detected tumors in 96% of positive patients but correctly left only 17% of healthy patients unflagged. It also required the pancreas location to be supplied before segmentation. Those results show both the potential of the approach and the two problems the capstone must address: too many false alarms and the need for autonomous localization.

The capstone need. The project will train and evaluate new models for the autonomous system, measure the accuracy lost when localization becomes automatic, and use model experimentation to improve the balance between detected tumors and false alarms. The previous result is evidence that motivates the work; the previous trained model will not be reused as the capstone model.

Supporting knowledge access. A connected literature assistant will retrieve relevant source passages for the structured imaging findings, show citations beside supported statements, and decline when the available material does not support an answer. This is a supporting workstream within the review workflow rather than the central modeling contribution.

Professional value. The deliverable is a reproducible system with known data history, controlled evaluation, recorded reviewer decisions, documented risks, and a usable interface. A difficult experiment may produce a null result; the system, evaluation process, and honest account of its limitations are not optional.

Scope guardrail. This is a segmentation and review-support system. It does not diagnose disease, determine treatment, or make a clinical claim.

# 3. Starting Point and New Capstone Work

The prior project contributes experience, failure analysis, and selected validated pipeline structure—not a completed model for the capstone. Data-preparation and evaluation components may be adapted where they remain appropriate, but no model trained during the preceding project will be reused as a capstone model. New models will be trained and evaluated under the capstone’s autonomous and multi-source design.

| Prior project provides | Capstone will produce |
| --- | --- |
| Experience preparing and evaluating 3D medical images | New models trained and evaluated for an autonomous system |
| A validated structure for data preparation and evaluation | A pipeline adapted for multiple data sources and the new experimental design |
| Documented experiments and lessons from approaches that succeeded or failed | Model experimentation selected from the new baseline and its measured errors |
| Knowledge of false alarms, data leakage, and dependence on a provided region | Patient-level evaluation designed around those known risks |
| Experience with model tracking, serving, and medical-image review | An integrated workflow built and evaluated for the capstone system |

## Multi-source integration in plain language

The imaging work will combine PanTS and PANORAMA. Their scans use compatible medical-image formats, but their labels, annotation quality, identifiers, and definitions of a negative case differ, and some scans may appear in both sources. Before combined data enters training or evaluation, the project will match records, remove known overlap, test for undeclared duplicates, record where each annotation came from, and keep every patient entirely within one data group. This prevents data leakage—the mistake of allowing information from an evaluation patient to influence training and make performance appear better than it really is. Detailed counts and reconciliation rules belong in the technical appendix.

# 4. Model Experimentation

The proposal commits to model experimentation, but it does not assume in advance which modeling strategy will be most useful. The autonomous baseline and its error analysis will determine the first experimental question. This keeps the project responsive to evidence instead of requiring a technique that may not address the measured failure mode.

Each experiment will begin with a written hypothesis, a fixed comparison, and a definition of what evidence would justify adopting the result. Training and evaluation data, preprocessing, and metrics will remain fixed unless one of those is the variable being studied. Major strategies will be evaluated separately so that any improvement or failure can be interpreted without several changes being mixed together.

Results will include pancreas and lesion overlap accuracy, patient-level tumor detection, and specificity—the percentage of healthy patients correctly left unflagged. The project will also compare the provided-region and autonomous conditions, examine important failure groups, and report uncertainty where the data support it. Model selection will be based on the full pattern of results rather than one favorable number.

What is promised. A fixed baseline, controlled comparisons, patient-level evaluation, and a documented decision. No particular modeling technique is promised to succeed.

# 5. Technical Approach and Applied AI Skills

- Medical-image machine learning — Python, PyTorch, and MONAI. Demonstrates 3D localization, segmentation, full-volume inference, and patient-level evaluation. Experience: Strong with the validated pipeline structure and evaluation process. Growth plan: Train new models, deepen autonomous localization and error analysis, and make model choices from evidence.

- Data integration and quality. Demonstrates combining datasets, matching records across sources, reconciling label meaning, tracking annotation origin, detecting duplicates, and protecting evaluation data. Experience: Experienced combining datasets and building reproducible data pipelines. Growth plan: Apply that experience to the project’s validation, provenance, and evaluation controls, and document the reconciliation evidence in the technical appendix.

- Relational and vector data storage. Demonstrates structured storage for scans, findings, model versions, reviewer decisions, and searchable literature. Experience: Solid with relational databases; less experience with vector search inside the same data layer. Growth plan: Create the data model before implementation, review it as a diagram, and validate retrieval against representative questions.

- Evidence-grounded applied AI. Demonstrates retrieval of relevant literature, visible source support, and refusal when retrieved material is insufficient. Experience: Familiar with retrieval and language-model workflows. Growth plan: Focus on measured retrieval quality, grounded responses, and safe system boundaries.

- Application integration — FastAPI, React, and NiiVue. Demonstrates a service connecting scan processing to a medical-image viewer, worklist, measurements, and saved review decisions. Experience: Strong with FastAPI and React; introductory experience with NiiVue. Growth plan: Apply that experience to the capstone interface and refine it through direct stakeholder feedback.

- MLOps and scalable compute — MLflow, Docker, and local or rented GPU resources. Demonstrates versioned experiments, reproducible environments, registered models, and scalable training. Experience: Strong with experiment tracking and containers; less experience budgeting rented GPU training. Growth plan: Benchmark hardware first, set a spending ceiling, record cost per experiment, and stop rental use if the throughput benefit does not justify the expense.

- Experimental methodology and governance. Demonstrates controlled comparisons, error analysis, reproducibility, limitation reporting, and human review of proposed contours. Experience: Strong after applying these practices in the preceding project. Growth plan: Apply the same discipline across model, retrieval, and system evaluation, with no diagnostic claims.

# 6. Ten-Week Delivery Plan

The plan targets completion of the committed system by the end of Week 8, leaving Week 9 as protected buffer and stabilization time and Week 10 for delivery and presentation. UI and UX refinement has dedicated work in Week 7. Unit tests are added with each component, followed by full unit, integration, and regression testing in Week 8. Stretch work will not consume the buffer.

| Wk | Primary focus | Planned work | Measurable deliverable | Behind-schedule signal |
| --- | --- | --- | --- | --- |
| 1 | Architecture and test planning | Confirm data design, retrieval requirements, workflow DAG, UI-extension requirements, and the unit/integration test strategy. | Approved architecture, acceptance criteria, workflow design, and test plan. | Data, retrieval, orchestration, or test criteria remain unresolved. |
| 2 | Protected data splits | Reproduce cohorts and add unit tests for patient separation, manifests, and repeatability. | Frozen cohorts with passing tests for patient separation, manifest validity, and reproducibility. | A patient can cross groups or a data-control test fails. |
| 3 | Second-source integration | Integrate PANORAMA with tested label mapping, provenance, exclusions, and duplicate controls. | Validated source integration with documented exclusions and passing reconciliation tests. | Source differences or exclusions cannot be explained or tested. |
| 4 | Unified pipeline and orchestration | Produce reproducible training inputs and implement the tested preprocessing and workflow DAG. | Reproducible training inputs and a tested, restartable workflow DAG. | A pipeline stage cannot be reproduced, tested, or safely restarted. |
| 5 | Autonomous baseline and retrieval foundation | Establish the imaging baseline; use model-training time to ingest literature and create the retrieval-index prototype. | Held-out baseline, error analysis, and a versioned, queryable retrieval prototype. | The baseline cannot run end to end or the retrieval prototype is not queryable. |
| 6 | Model experiment and retrieval evaluation | Complete one controlled model comparison, evaluate the false-alarm tradeoff, and measure retrieval quality. | Documented model decision, operating-point results, and retrieval metrics. | The model result is not comparable or retrieval quality cannot be measured. |
| 7 | UI refinement and stakeholder review | Extend the existing interface, integrate representative model/evidence outputs, and conduct stakeholder review. | Integrated review flow and documented stakeholder feedback. | The accept/edit/reject flow is not usable or stakeholder feedback is unavailable. |
| 8 | Integration, testing, and evaluation | Complete end-to-end integration, full unit/integration/regression testing, held-out evaluation, and documentation drafts. | End-to-end demonstration, passing test suite, locked metrics, and documentation drafts. | A core path requires manual operation, tests fail, or evaluation is incomplete. |
| 9 | Protected buffer and stabilization | Absorb overruns, correct defects, rerun affected tests or evaluation, and lock the release. No new scope. | Stable release candidate with resolved priority defects and rerun evidence. | A core blocker remains unresolved by the middle of the buffer week. |
| 10 | Delivery and presentation | Package the stable system, complete documentation, rehearse the demonstration, and present. | Submitted package, model card, user guidance, and presentation-ready demonstration. | Release changes extend beyond minor packaging or presentation corrections. |

## Scope control and stakeholder review

The committed scope is the autonomous imaging pipeline, validated multi-source data layer, controlled model experimentation, patient-level evaluation, recorded review workflow, evidence-grounded literature retrieval, and professional documentation. Optional work begins only after those capabilities are functioning and passing their tests. Week 9 is reserved for schedule recovery, defect correction, re-evaluation, and stabilization; Week 10 is reserved for delivery and presentation. Neither week is assigned to new stretch work.

## Stretch opportunities

The estimates below describe hands-on implementation time after the committed system is functioning and passing its tests. They do not include waiting for an outside reviewer, and no stretch opportunity is presented as a guaranteed improvement. Stretch work may begin only when it will not consume the protected Week 9 buffer or Week 10 delivery time.

| Stretch opportunity | Scope and potential benefit | Complexity | Estimated implementation effort |
| --- | --- | --- | --- |
| Further model experimentation | Run an additional evidence-driven comparison after the required baseline experiment, increasing the chance of finding a better accuracy or false-alarm tradeoff. | High | 1–2 weeks per additional experiment, including training, evaluation, and analysis. |
| Expanded text sources | Add PanTS text resources or broader literature coverage, then remeasure whether retrieval improves without reducing precision. | Medium | 3–5 working days for ingestion, indexing, and evaluation updates. |
| Richer report support | Draft a structured summary from accepted findings and evaluate whether every statement remains complete, editable, and grounded in available evidence. | Medium–High | 5–8 working days for generation, review controls, interface work, and evaluation. |
| External evaluation | Package the model, configuration, documentation, and outputs for an outside research team or hidden evaluation path. | Medium internally; high external dependency | 2–4 working days to package and verify; response time is outside the project’s control. |

Stakeholder plan. A diagnostic care coordinator has confirmed availability for the week 7 review session so feedback can shape the remaining work. A practicing radiologist is being arranged as the primary reviewer. If that is not available, the confirmed coordinator provides a real clinical-workflow perspective while the limitation is disclosed.

# 7. Professional Growth and Readiness

The capstone challenges me beyond the preceding project in several ways. I must deepen my medical-imaging knowledge, work with multiple large data sources, design reliable data controls, remove a human-provided region from the model workflow, train new models, and connect modeling, retrieval, persistence, automation, and user review into one coherent system. The challenge is not merely writing more code. It is deciding which evidence matters, resisting attractive but unsupported conclusions, and making technical choices that remain understandable to a reviewer.

The most important professional growth will come from managing uncertainty. Model experimentation does not guarantee improvement, and the autonomous system may perform worse than the provided-region reference. My responsibility is to design fair comparisons, adapt the next experiment to the measured failure mode, control time and compute costs, and report the result honestly. Completing that process at this scale will strengthen me as both an AI practitioner and a technical decision-maker.